## Expanded Tasks
ID | Name | % Complete | Start | Finish | Resources | Estimated | Actual
11 | 02/11/2020 - Setup Github repository | 100% | 2020-02-11 | 2020-02-11 | Jon | 0.5 | 0.5
12 | 02/11/2020 - Create README template | 100% | 2020-02-11 | 2020-02-11 | Jon | 0.5 | 0.5
10 | 02/12/2020 - Create WBS / GANTT template | 100% | 2020-02-12 | 2020-02-12 | Jon | 1 | 1
3 | 02/13/2020 - Research chatbot algorithms | 100% | 2020-02-11 | 2020-02-13 | Michael | 4 | 4
3 | 02/13/2020 - Research chatbot algorithms | 100% | 2020-02-11 | 2020-02-13 | Shamus | 4 | 4
5 | 02/15/2020 - Create base application | 100% | 2020-02-15 | 2020-02-15 | Jaden | 1 | 1
13 | 02/16/2020 - Write wiki page for react.js | 100% | 2020-02-15 | 2020-02-16 | Jaden | 0.5 | 1
7 | 02/17/2020 - Run base application | 100% | 2020-02-17 | 2020-02-17 | Michael | 0.5 | 0.5
20 | 02/18/2020 - Design high-level processing algorithm | 100% | 2020-02-18 | 2020-02-18 | Jaden | 1.5 | 1.5
20 | 02/18/2020 - Design high-level processing algorithm | 100% | 2020-02-18 | 2020-02-18 | Michael | 1.5 | 1.5
20 | 02/18/2020 - Design high-level processing algorithm | 100% | 2020-02-18 | 2020-02-18 | Shamus | 1.5 | 1.5
17 | 02/22/2020 - Sample conversation 1 | 100% | 2020-02-22 | 2020-02-22 | Michael | 1 | 1.5
23 | 02/22/2020 - Implement text input processing | 100% | 2020-02-21 | 2020-02-22 | Shamus | 3 | 4
22 | 02/23/2020 - Implement text pre-processing | 100% | 2020-02-23 | 2020-02-23 | Jaden | 2 | 3
16 | 02/24/2020 - Setup web server to host production site | 100% | 2020-02-24 | 2020-02-24 | Jon | 2 | 3
18 | 02/24/2020 - Initial text file for output tree | 100% | 2020-02-24 | 2020-02-24 | Michael | 0.5 | 0.5
27 | 02/24/2020 - Add SDLC rational to project document | 100% | 2020-02-24 | 2020-02-24 | Jon | 0.5 | 0.5
25 | 02/25/2020 - Test web hosting | 100% | 2020-02-24 | 2020-02-25 | Jaden | 0.5 | 0.5
32 | 02/26/2020 - Text mapping algorithm | 100% | 2020-02-26 | 2020-02-26 | Shamus | 3 | 3
33 | 02/27/2020 - Basic text input and output UI | 100% | 2020-02-27 | 2020-02-27 | Shamus | 2 | 1
34 | 02/27/2020 - Output generation | 100% | 2020-02-27 | 2020-02-27 | Shamus | 1 | 1
40 | 02/27/2020 - Add description to document | 100% | 2020-02-27 | 2020-02-27 | Jon | 0.5 | 0.5
43 | 02/27/2020 - Add list of limitations to document | 100% | 2020-02-27 | 2020-02-27 | Michael | 0.5 | 0.5
36 | 02/28/2020 - Test and prepare for 30 turn conversation | 100% | 2020-02-28 | 2020-02-28 | Michael | 1 | 2
44 | 02/28/2020 - Populate sample output file in Github | 100% | 2020-02-28 | 2020-02-28 | Michael | 0.5 | 0.5
30 | 03/02/2020 - Align requirements with deliverables | 100% | 2020-03-02 | 2020-03-02 | Jon | 1 | 1
37 | 03/02/2020 - Test and review code changes | 100% | 2020-03-02 | 2020-03-02 | Jaden | 1 | 3
41 | 03/02/2020 - Add SDLC phases / tasks to document | 100% | 2020-03-02 | 2020-03-02 | Jon | 1 | 1
42 | 03/02/2020 - Add final WBS / GANTT to document | 100% | 2020-03-02 | 2020-03-02 | Jon | 1 | 1
45 | 03/02/2020 - Add Github commits by user | 100% | 2020-03-02 | 2020-03-02 | Michael | 0.5 | 0.5
46 | 03/03/2020 - Finalize README file in Github repository | 100% | 2020-03-02 | 2020-03-03 | Jon | 2 | 1.5
49 | 03/04/2020 - Learn natural NLP functionality and use | 100% | 2020-03-03 | 2020-03-04 | Shamus | 3 | 3
49 | 03/04/2020 - Learn natural NLP functionality and use | 100% | 2020-03-03 | 2020-03-04 | Michael | 3 | 3
53 | 03/08/2020 - Add weighted logic to selection from response list | 100% | 2020-03-08 | 2020-03-08 | Jaden | 1 | 0.5
54 | 03/08/2020 - Save history of past responses | 100% | 2020-03-08 | 2020-03-08 | Jaden | 1 | 0.5
50 | 03/09/2020 - Research neural net/machine learning | 100% | 2020-03-08 | 2020-03-09 | Michael | 2 | 1
52 | 03/09/2020 - User input NLP pre-processing | 100% | 2020-03-08 | 2020-03-09 | Michael | 2 | 2
55 | 03/09/2020 - Start advanced GUI | 100% | 2020-03-09 | 2020-03-09 | Jon | 3 | 4
61 | 03/10/2020 - Update isQuestion method | 100% | 2020-03-10 | 2020-03-10 | Shamus | 1 | 1
62 | 03/14/2020 - Add server-side express functionality | 100% | 2020-03-14 | 2020-03-14 | Jaden | 3 | 3
59 | 03/15/2020 - Learn about slack integration | 100% | 2020-03-15 | 2020-03-15 | Shamus | 4 | 4
58 | 03/16/2020 - Learn about React states and components | 100% | 2020-03-16 | 2020-03-16 | Jon | 2 | 4
63 | 03/16/2020 - Add scroll bar to chat UI | 100% | 2020-03-16 | 2020-03-16 | Jon | 0.5 | 0.5
64 | 03/16/2020 - Finalize UI message styling | 100% | 2020-03-16 | 2020-03-16 | Jon | 1.5 | 3
74 | 03/17/2020 - Implement component-based GUI | 100% | 2020-03-17 | 2020-03-17 | Jon | 2 | 3
74 | 03/17/2020 - Implement component-based GUI | 100% | 2020-03-17 | 2020-03-17 | Jaden | 2 | 3
75 | 03/17/2020 - Integrate GUI with server-side functionality | 100% | 2020-03-17 | 2020-03-17 | Jaden | 1 | 2
70 | 03/18/2020 - Connect GUI to message history | 100% | 2020-03-18 | 2020-03-18 | Jon | 1 | 2
71 | 03/18/2020 - Add auto-scroll function to GUI | 100% | 2020-03-18 | 2020-03-18 | Jon | 1 | 1
77 | 03/18/2020 - Test and troubleshoot new master branch | 100% | 2020-03-18 | 2020-03-18 | Jon | 1 | 3
69 | 03/19/2020 - Implement Slack chat-bot integration | 100% | 2020-03-19 | 2020-03-19 | Shamus | 3 | 3
72 | 03/19/2020 - Implement natural functions server-side | 100% | 2020-03-19 | 2020-03-19 | Michael | 2 | 2
67 | 03/20/2020 - Design advanced response mapping | 100% | 2020-03-20 | 2020-03-20 | Michael | 3 | 3
67 | 03/20/2020 - Design advanced response mapping | 100% | 2020-03-20 | 2020-03-20 | Jaden | 3 | 3
78 | 03/21/2020 - Test natural functions server-side | 100% | 2020-03-21 | 2020-03-21 | Michael | 1 | 1
73 | 03/23/2020 - Expand tree node input functionality | 100% | 2020-03-23 | 2020-03-23 | Jaden | 1 | 1
85 | 03/24/2020 - Add synonyms to language processing | 100% | 2020-03-24 | 2020-03-24 | Michael | 5 | 2
85 | 03/24/2020 - Add synonyms to language processing | 100% | 2020-03-24 | 2020-03-24 | Jaden | 5 | 2
81 | 03/26/2020 - Add extra topic to agent repetoire | 100% | 2020-03-26 | 2020-03-26 | Michael | 1 | 1
81 | 03/26/2020 - Add extra topic to agent repetoire | 100% | 2020-03-26 | 2020-03-26 | Jaden | 1 | 1
82 | 03/27/2020 - Add 5 non-topic related responses | 100% | 2020-03-27 | 2020-03-27 | Michael | 0.5 | 0.5
84 | 03/27/2020 - Implement feature to handle spelling mistakes | 100% | 2020-03-26 | 2020-03-27 | Michael | 1 | 1
84 | 03/27/2020 - Implement feature to handle spelling mistakes | 100% | 2020-03-26 | 2020-03-27 | Jaden | 1 | 1
89 | 03/29/2020 - Add list of 5 features that can be used as API | 100% | 2020-03-29 | 2020-03-29 | Jaden | 1 | 1
90 | 03/29/2020 - Walk through of each feature in README file | 0% | 2020-03-29 | 2020-03-29 | Michael | 3 | 3
90 | 03/29/2020 - Walk through of each feature in README file | 0% | 2020-03-29 | 2020-03-29 | Jaden | 3 | 3
87 | 03/30/2020 - Test pre-processing for bugs | 100% | 2020-03-30 | 2020-03-30 | Jon | 0.5 | 0.5
91 | 03/30/2020 - Provide level 0 DFD | 100% | 2020-03-30 | 2020-03-30 | Jon | 2 | 1
92 | 03/30/2020 - Provide level 1 DFD | 100% | 2020-03-30 | 2020-03-30 | Jon | 2 | 3
94 | 03/30/2020 - Begin writing script | 0% | 2020-03-30 | 2020-03-30 | Shamus | 1 | 1
98 | 03/31/2020 - Fix bugs found in pre-processing test | 100% | 2020-03-31 | 2020-03-31 | Jaden | 1 | 1
107 | 04/02/2020 - Create and edit a 60 to 90 second video | 100% | 2020-04-02 | 2020-04-02 | Shamus | 3 | 3
108 | 04/02/2020 - Description of the conversational topic | 100% | 2020-04-02 | 2020-04-02 | Shamus | 1 | 1
109 | 04/02/2020 - Show each feature and how it adds to system | 100% | 2020-04-02 | 2020-04-02 | Shamus | 1 | 1
110 | 04/02/2020 - Desciption of the data flow diagrams | 100% | 2020-04-02 | 2020-04-02 | Shamus | 1 | 1
97 | 04/03/2020 - Increase conversation repertoire / capability | 100% | 2020-04-03 | 2020-04-03 | Michael | 2 | 2
97 | 04/03/2020 - Increase conversation repertoire / capability | 100% | 2020-04-03 | 2020-04-03 | Jaden | 2 | 2
102 | 04/03/2020 - Update README file in Github | 100% | 2020-04-03 | 2020-04-03 | Michael | 3 | 3
102 | 04/03/2020 - Update README file in Github | 100% | 2020-04-03 | 2020-04-03 | Jaden | 3 | 3
103 | 04/03/2020 - Add Github link and commits by user | 100% | 2020-04-03 | 2020-04-03 | Jon | 0.5 | 0.5
104 | 04/03/2020 - Finalize and submit documentation | 100% | 2020-04-03 | 2020-04-03 | Jon | 3 | 3
105 | 04/03/2020 - Add list of limitations to document | 100% | 2020-04-03 | 2020-04-03 | Michael | 0.5 | 0.5
100 | 04/04/2020 - Test and deploy final version on production server | 100% | 2020-04-04 | 2020-04-04 | Jon | 1 | 1

## Pivot Summary
Task Description | Estimated Hours | Actual Hours
Jaden | 35.5 | 37
02/15/2020 - Create base application | 1 | 1
02/16/2020 - Write wiki page for react.js | 0.5 | 1
02/18/2020 - Design high-level processing algorithm | 1.5 | 1.5
02/23/2020 - Implement text pre-processing | 2 | 3
02/25/2020 - Test web hosting | 0.5 | 0.5
03/02/2020 - Test and review code changes | 1 | 3
03/08/2020 - Add weighted logic to selection from response list | 1 | 0.5
03/08/2020 - Save history of past responses | 1 | 0.5
03/14/2020 - Add server-side express functionality | 3 | 3
03/17/2020 - Implement component-based GUI | 2 | 3
03/17/2020 - Integrate GUI with server-side functionality | 1 | 2
03/20/2020 - Design advanced response mapping | 3 | 3
03/23/2020 - Expand tree node input functionality | 1 | 1
03/24/2020 - Add synonyms to language processing | 5 | 2
03/26/2020 - Add extra topic to agent repetoire | 1 | 1
03/27/2020 - Implement feature to handle spelling mistakes | 1 | 1
03/29/2020 - Add list of 5 features that can be used as API | 1 | 1
03/29/2020 - Walk through of each feature in README file | 3 | 3
03/31/2020 - Fix bugs found in pre-processing test | 1 | 1
04/03/2020 - Increase conversation repertoire / capability | 2 | 2
04/03/2020 - Update README file in Github | 3 | 3
Jon | 31 | 40
02/11/2020 - Setup Github repository | 0.5 | 0.5
02/11/2020 - Create README template | 0.5 | 0.5
02/12/2020 - Create WBS / GANTT template | 1 | 1
02/24/2020 - Setup web server to host production site | 2 | 3
02/24/2020 - Add SDLC rational to project document | 0.5 | 0.5
02/27/2020 - Add description to document | 0.5 | 0.5
03/02/2020 - Align requirements with deliverables | 1 | 1
03/02/2020 - Add SDLC phases / tasks to document | 1 | 1
03/02/2020 - Add final WBS / GANTT to document | 1 | 1
03/03/2020 - Finalize README file in Github repository | 2 | 1.5
03/09/2020 - Start advanced GUI | 3 | 4
03/16/2020 - Learn about React states and components | 2 | 4
03/16/2020 - Add scroll bar to chat UI | 0.5 | 0.5
03/16/2020 - Finalize UI message styling | 1.5 | 3
03/17/2020 - Implement component-based GUI | 2 | 3
03/18/2020 - Connect GUI to message history | 1 | 2
03/18/2020 - Add auto-scroll function to GUI | 1 | 1
03/18/2020 - Test and troubleshoot new master branch | 1 | 3
03/30/2020 - Test pre-processing for bugs | 0.5 | 0.5
03/30/2020 - Provide level 0 DFD | 2 | 1
03/30/2020 - Provide level 1 DFD | 2 | 3
04/03/2020 - Add Github link and commits by user | 0.5 | 0.5
04/03/2020 - Finalize and submit documentation | 3 | 3
04/04/2020 - Test and deploy final version on production server | 1 | 1
Michael | 39 | 36.5
02/13/2020 - Research chatbot algorithms | 4 | 4
02/17/2020 - Run base application | 0.5 | 0.5
02/18/2020 - Design high-level processing algorithm | 1.5 | 1.5
02/22/2020 - Sample conversation 1 | 1 | 1.5
02/24/2020 - Initial text file for output tree | 0.5 | 0.5
02/27/2020 - Add list of limitations to document | 0.5 | 0.5
02/28/2020 - Test and prepare for 30 turn conversation | 1 | 2
02/28/2020 - Populate sample output file in Github | 0.5 | 0.5
03/02/2020 - Add Github commits by user | 0.5 | 0.5
03/04/2020 - Learn natural NLP functionality and use | 3 | 3
03/09/2020 - Research neural net/machine learning | 2 | 1
03/09/2020 - User input NLP pre-processing | 2 | 2
03/19/2020 - Implement natural functions server-side | 2 | 2
03/20/2020 - Design advanced response mapping | 3 | 3
03/21/2020 - Test natural functions server-side | 1 | 1
03/24/2020 - Add synonyms to language processing | 5 | 2
03/26/2020 - Add extra topic to agent repetoire | 1 | 1
03/27/2020 - Add 5 non-topic related responses | 0.5 | 0.5
03/27/2020 - Implement feature to handle spelling mistakes | 1 | 1
03/29/2020 - Walk through of each feature in README file | 3 | 3
04/03/2020 - Increase conversation repertoire / capability | 2 | 2
04/03/2020 - Update README file in Github | 3 | 3
04/03/2020 - Add list of limitations to document | 0.5 | 0.5
Shamus | 32.5 | 32.5
02/13/2020 - Research chatbot algorithms | 4 | 4
02/18/2020 - Design high-level processing algorithm | 1.5 | 1.5
02/22/2020 - Implement text input processing | 3 | 4
02/26/2020 - Text mapping algorithm | 3 | 3
02/27/2020 - Basic text input and output UI | 2 | 1
02/27/2020 - Output generation | 1 | 1
03/04/2020 - Learn natural NLP functionality and use | 3 | 3
03/10/2020 - Update isQuestion method | 1 | 1
03/15/2020 - Learn about slack integration | 4 | 4
03/19/2020 - Implement Slack chat-bot integration | 3 | 3
03/30/2020 - Begin writing script | 1 | 1
04/02/2020 - Create and edit a 60 to 90 second video | 3 | 3
04/02/2020 - Description of the conversational topic | 1 | 1
04/02/2020 - Show each feature and how it adds to system | 1 | 1
04/02/2020 - Desciption of the data flow diagrams | 1 | 1
Grand Total | 138 | 146